## Slide 1
DAK: “Does AI Know”?
Scope: Create DAK app to perform predictions for various scenarios by utilising machine learning algorithms, python libraries with front end UI and host on a cloud platform with public access
Team Members:
  Daniela Cornea (DC)
  Anh Huong (AH)
  Kevin Nguyen (KN)
Project repo: https://github.com/DCornea5/Final-Project.git
Project “DAK”

## Slide 2
Methods: Flask API, HTML/CSS/Boostrap, Matplotlib, Tableau, Heroku, github, etc…
Dataset:
  heart_disease.csv
  Stress-Lysis.csv
  bodyPerformance.csv
  TravelInsurancePredictions.csv
  Absenteeism_at_work2.csv
Sources:
  Kaggle, https://www.kaggle.com/code/ahmedklabi/heart-disease-pred/data
  Dataworld, https://data.world/aaizemberg/absenteeismatwork/workspace/file?filename=Absenteeism_at_work.tsv
Methods

## Slide 3
Project High Level Requirements

## Slide 4
User Interface
Option1
OptionN
ML Models
Mod_1
Mod_N
Data
EDA/ Pre-processing
Algorithm
Option2
Option3
Predictor
High Level Design

## Slide 5
Research project topic and select datasets on various sources
Create project plan and github repo
Project is adopting Agile methodology for software development:
  Iterations of design, coding, testing for the app’s front and back-end.
  Minimum viable product (MVP): a working machine learning model (ML) with user interface (UI) front end that hosted on a cloud platform
  Product: a completed a scalable front end web site with various ML models that hosted on a cloud platform.
On-going task allocations: self-manage, support other team members as required
Project presentation
Documentations:
  Project docs, reports
  Presentation pack
Project Plan

## Slide 6
Date | Task # | Descriptions | Status
8/4 | 0 | Form the project team | Completed
10/4 18/4 | 1 | Select project topic Select datasets on various open sources ML models - perform exploratory data analysis(EDA), build, test, measure and save the models: Stroke prediction Body performance prediction Stress level prediction Travel Insurance prediction Polygon shape prediction (WIP) | Completed
19/4 | 2 | High level design Present project proposal to instructors | 
20/4 | 3 | Front-end web site design | 
30/4 | 4 | Completed web-site design | 
1/5 | 5 | Finalise platform deployment End-to-end test | 
2/5 | 6 | Presentation rehearsal | 
3/5 | 7 | Project presentation Project submission | 
Project Schedules & Milestones

## Slide 7
Challenges
Performed EDA on datasets
  Zomato Restaurant Reviews.
    Outcome: Unable to utilise on the project as the data is heavily skewed for the restaurants in India
  Absenteeism at work.
    Outcome: Applied 12 different ML methods, 17 out of 21 columns are seemed relevant. Not user friendly as too many fields are required user input
  etc…adfafd
  Etc…